## Sheet1
issue # number | describtion | Notes | start at | end at | 1 | 2 | 3 | 4 | 5 | 6 | 7
#78 | Control Stop/Start Faculty LMS sync | No test cases | 16-12-2025 | 16-12-2025
#79 | Install and configure IMS and SIS for demo | No test cases | 16-12-2025 | 16-12-2025
#73 | Prevent access/action to any record |  |  |  | 1: eng account could access medicine student excuse [solved]
#74 | Implement cancel approval for applicants | No test cases | 16-12-2025 | 16-12-2025
#75 | Implement payment for Students Activities |  |  |  | 1: end date could be before start date [solved]; 2: ui has 2 filters "Select Term" [solved]; 3: students can't access activities list VALIDATION ERROR-> pending activity is shown to students, also open one not showed; 4: all roles are set to moustafa.business@nasu.edu.eg to access students activities but he cant
#76 | Students Activities | related to #75 | 16-12-2025
#77 | Implement Query Modifier for Ambiguous Columns | No test cases | 16-12-2025 | 16-12-2025
#81 | Changes to Students Activities | related to #75 | 16-12-2025
#63 | Implement user access on Certificates and eServices |  |  |  | 1: certificate list not available [resolved]; 2: exception during accept the request of certificate at emp account; 3: moustafa.medicine@yahoo.com hasn't students activities in the sidebar also he has an access activities permission
#86 | Can't Add New Term | solved | 17-12-2025
#72 | Implement latest questionnaire updates | reopened | 17-12-2025 |  | 1: need to display the questionnaire faculty; 2: Update Questionnairy Modal doesn't retrieve the faculty - The modal need a field name above the field with * for required one -
#73 | Prevent access/action to any record | closed | 16-12-2025 | 18-12-2025 | 1: eng account could access medicine student excuse [solved]
#89 | Edit term is failing | reopened | 28-12-2025 |  | 1: 404 NOT Found through edit the term